## Overview
Civant Production Ramp Execution Board (Option B)
Purpose | Track the 6-week balanced production ramp across data quality, freshness, product value loop, predictions, security, and launch readiness.
Start date | 2026-02-12
Target window | 4-6 weeks
Primary owner | David + Atlas
Execution Phases
Week | Theme | Scope
Week 1 | Data Acceptance Gate | Duplicate rate, completeness, CPV coverage, notice normalization, country/source consistency
Week 2 | Freshness + Monitoring | Incremental jobs, retries, alerts, lag/success SLOs
Week 3 | V1 User Value Loop | Saved searches, alerts, competitor watch, evidence links
Week 4 | Prediction Trust Layer | Confidence breakdown, drivers, evidence, country validation report
Week 5 | Security + Observability | RLS/RBAC checks, API telemetry, error budget, log quality
Week 6 | Launch Readiness | Go/no-go gates, rollback runbook, KPI baseline and live checklist

## Tasks
ID | Week | Phase | Workstream | Task | Owner | Priority | Dependencies | Acceptance Criteria | KPI / Target | Status | % Complete | Evidence | Notes
W1-01 | Week 1 | Data Acceptance Gate | Quality | Generate IE/FR/ES completeness report for critical fields | Atlas | P0 | Spain core load complete | Country report exists and reviewed | >95% critical completeness | Not Started | 0
W1-02 | Week 1 | Data Acceptance Gate | Quality | Run duplicate analysis by source+external_id and canonical_id | Atlas | P0 | W1-01 | Duplicate report published by country/source | <2% duplicate rate | Not Started | 0
W1-03 | Week 1 | Data Acceptance Gate | Quality | Validate CPV parse coverage and malformed CPV counts | Atlas | P0 | W1-01 | CPV coverage report with top errors | >90% coverage | Not Started | 0
W1-04 | Week 1 | Data Acceptance Gate | Normalization | Notice-type mapping incl. Corrigendum coverage | Atlas | P1 | W1-01 | Normalized notice taxonomy approved | 100% mapped | Not Started | 0
W1-05 | Week 1 | Data Acceptance Gate | Governance | Approve data gate thresholds for production | David | P0 | W1-01,W1-02,W1-03,W1-04 | Signed-off threshold table | Gate approved | Not Started | 0
W2-01 | Week 2 | Freshness + Monitoring | Ingestion | Schedule incremental connector jobs (IE/FR/ES) | Atlas | P0 | W1-05 | Jobs deployed with schedules | All 3 active | Not Started | 0
W2-02 | Week 2 | Freshness + Monitoring | Reliability | Implement retry policy + dead-letter handling | Atlas | P0 | W2-01 | Retries and DLQ visible in run logs | <2% unrecovered failures | Not Started | 0
W2-03 | Week 2 | Freshness + Monitoring | Observability | Build ingestion run dashboard with lag/success metrics | Atlas | P1 | W2-01 | Dashboard used for daily checks | Success >98%, lag <6h | Not Started | 0
W2-04 | Week 2 | Freshness + Monitoring | Alerting | Create failure alerts (Slack/email) for run failures | Atlas | P1 | W2-03 | Alert tested via simulated failure | <15 min detection | Not Started | 0
W2-05 | Week 2 | Freshness + Monitoring | Ops | Run 7-day soak test with incident log | David | P0 | W2-01,W2-02,W2-03,W2-04 | No silent failure during soak | 7-day pass | Not Started | 0
W3-01 | Week 3 | V1 User Value Loop | Product | Finalize saved search UX and persistence | Atlas | P1 | W2-05 | Search criteria save/restore works | 100% pass in QA | Not Started | 0
W3-02 | Week 3 | V1 User Value Loop | Product | Alerts trigger pipeline from saved search conditions | Atlas | P0 | W3-01 | Triggered alerts visible and actionable | Trigger latency <10 min | Not Started | 0
W3-03 | Week 3 | V1 User Value Loop | Product | Competitor watchlist updates and activity feed | Atlas | P1 | W3-02 | Competitor entity tracking works end-to-end | No P1 defects | Not Started | 0
W3-04 | Week 3 | V1 User Value Loop | UX | Country/source flags and labels audit on key pages | Atlas | P1 | W3-01 | No mislabelled country/source in QA sample | 100% correct in sample | Not Started | 0
W3-05 | Week 3 | V1 User Value Loop | Validation | End-to-end user journey test (search -> alert -> evidence) | David | P0 | W3-01,W3-02,W3-03 | Recorded walkthrough passes | Journey pass | Not Started | 0
W4-01 | Week 4 | Prediction Trust Layer | Model | Implement confidence breakdown (data/signal/model) | Atlas | P0 | W2-05 | Breakdown rendered for each prediction | 100% predictions with breakdown | Not Started | 0
W4-02 | Week 4 | Prediction Trust Layer | Model | Attach top drivers and evidence links in UI | Atlas | P0 | W4-01 | Top drivers displayed with evidence | >=5 drivers when available | Not Started | 0
W4-03 | Week 4 | Prediction Trust Layer | Evaluation | Country-level prediction quality report | Atlas | P1 | W4-01,W4-02 | Evaluation report reviewed | Quality baseline approved | Not Started | 0
W4-04 | Week 4 | Prediction Trust Layer | Governance | Define no-black-box rule in release checklist | David | P1 | W4-02 | Checklist item enforced in QA | Policy active | Not Started | 0
W5-01 | Week 5 | Security + Observability | Security | RLS policy audit and regression tests | Atlas | P0 | W2-05 | No critical RLS gaps | 0 critical findings | Not Started | 0
W5-02 | Week 5 | Security + Observability | Security | RBAC endpoint enforcement review | Atlas | P0 | W5-01 | Admin/user/creator tests pass | 100% auth matrix pass | Not Started | 0
W5-03 | Week 5 | Security + Observability | Observability | API p95 latency + 5xx dashboards | Atlas | P1 | W2-03 | Dashboards available with alerts | p95 within target | Not Started | 0
W5-04 | Week 5 | Security + Observability | Reliability | Structured logging standardization | Atlas | P1 | W5-03 | Logs include run_id/tenant/source consistently | >95% log completeness | Not Started | 0
W5-05 | Week 5 | Security + Observability | Risk | Dependency vulnerability triage | Atlas | P1 | W5-01 | Critical/high vulns triaged | 0 untriaged critical | Not Started | 0
W6-01 | Week 6 | Launch Readiness | Operations | Create go/no-go checklist and owners | Atlas | P0 | W5-05 | Checklist approved by David | Checklist complete | Not Started | 0
W6-02 | Week 6 | Launch Readiness | Operations | Rollback + incident runbook drill | Atlas | P0 | W6-01 | Dry run executed successfully | Recovery time verified | Not Started | 0
W6-03 | Week 6 | Launch Readiness | Product | Finalize demo script and key scenarios | David | P1 | W3-05,W4-03 | Demo script approved | Demo pass | Not Started | 0
W6-04 | Week 6 | Launch Readiness | Analytics | Baseline KPI dashboard for launch cohort | Atlas | P1 | W6-01 | KPI dashboard live | Daily tracking active | Not Started | 0
W6-05 | Week 6 | Launch Readiness | Decision | Go/No-Go meeting + decision log | David | P0 | W6-01,W6-02,W6-03,W6-04 | Decision documented | Launch decision made | Not Started | 0

## KPI_Gates
Gate | Metric | Threshold | Current | Status | Owner | Evidence
Data Gate | Critical-field completeness | >95% |  | Not Started | Atlas
Data Gate | Duplicate rate | <2% |  | Not Started | Atlas
Data Gate | CPV coverage | >90% |  | Not Started | Atlas
Freshness Gate | 7-day connector success | >98% |  | Not Started | Atlas
Freshness Gate | Median lag | <6h |  | Not Started | Atlas
Trust Gate | Predictions with confidence breakdown | 100% |  | Not Started | Atlas
Trust Gate | Predictions with evidence links | 100% |  | Not Started | Atlas
Security Gate | Critical RLS findings | 0 |  | Not Started | Atlas
Security Gate | RBAC matrix pass | 100% |  | Not Started | Atlas
Ops Gate | Rollback drill success | Pass |  | Not Started | Atlas

## Risks_Issues
ID | Type | Description | Impact | Likelihood | Mitigation | Owner | Status | Due
R-01 | Risk | Connector source schema drift breaks parsers | High | Medium | Add schema-drift detector + fallback parser | Atlas | Open | 2026-02-20
R-02 | Risk | Prediction trust low without evidence consistency | High | Medium | Block release if confidence/evidence missing | David | Open | 2026-03-05
R-03 | Issue | Long-running backfills increase operational load | Medium | Medium | Use staged COPY + incremental-only production mode | Atlas | Open | 2026-02-18
R-04 | Risk | RLS regressions with new tables/migrations | High | Low | RLS regression suite in CI + weekly audit | Atlas | Open | 2026-03-10

## Milestones
Milestone | Target Week | Definition of Done | Owner | Status
Data Gate Approved | Week 1 | All data gate metrics reviewed and approved | David | Not Started
Freshness SLO Stable | Week 2 | 7-day >98% connector success, lag <6h | Atlas | Not Started
V1 Value Loop Complete | Week 3 | Search-alert-competitor flow QA passed | Atlas | Not Started
Prediction Trust v1 | Week 4 | Confidence + evidence rendered for all predictions | Atlas | Not Started
Security Hardening Complete | Week 5 | RLS/RBAC checks green, no critical findings | Atlas | Not Started
Launch Go/No-Go | Week 6 | Checklist complete + decision documented | David | Not Started